## Report
Test Case Report
Project Name |  | Etsy |  |  |  | Total No. | Status | Result:
Test Case Version | [5 empty] | 66 | PASS
Written By |  | Mysara Nur Tanha |  |  |  | 5 | FAIL
Executed By |  | Mysara Nur Tanha |  |  |  | 0 | Not Executed | New Features | Testing Scope | Testing Environment: | Google Chrome Browser
Reviewed By | [5 empty] | 0 | Out of Scope
Test Execution Report
Test Case | Pass | Fail | Not Executed | Out of Scope | Total TC
| 26 | 5 | 0 | 0 | 31
Grand Total | 26 | 5 | 0 | 0 | 31
Limitations
Documents |  |  |  | Recieved | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
|  | Testing type in scope |  | Description
Yes/ No Justification (if No): |  | Functional Testing |  | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No Justification (if No): |  | Integration Testing |  | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No Justification (if No): |  | Negative Testing |  | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No Justification (if No): |  | Usability Testing |  | Test application from user friendliness perspective.
Yes/ No Justification (if No): |  | Browser Compatibility Testing |  | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No Justification (if No): |  | Boundary Value Testing |  | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No Justification (if No): |  | Risk Based Testing Or Regression Testing |  | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Test Case
Product Name |  | Etsy | TC Start Date | 2025-01-03 | TC Execution Start Date | 2025-01-03 |  |  |  |  | Test Case
Module Name |  |  | TC End Date | 2025-01-03 | TC Execution End Date | 2025-01-03 |  |  |  |  | PASS | 26
Epic |  |  | Test Case Developed By | Mysara Nur Tanha | Browser (tested) | Yes |  |  |  |  | FAIL | 5
Developer Name |  |  | Test Case Reviewed By |  | Performance (tested) | Yes |  |  |  |  | Not Executed | 0
Test Executed By |  | Mysara Nur Tanha | [8 empty] | Out of Scope | 0
[11 empty] | Total | 31
#SL | Module | Type of Testing | Features | Test Cases | Expected Result | Actual Result | Test Data | Reproducing Steps | Big Screenshot | Dev Comments | Final Status | Remarks
1 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | N/A |  |  |  | Passed
2 | Notifications | Functionality Testing | Order Updates | Verify that order updates are sent to the user. | User should receive order updates notification. | Found as per expectation | N/A | 1. Login to the application as a registered user. 2. Navigate to the "Orders" section. 3. Place an order. 4. Wait for an update regarding the order (e.g., status change). 5. Check for a notification regarding the update. |  |  | Passed
3 |  |  | Promotional Emails | Verify that promotional emails are sent. | User should receive promotional emails. | Found as per expectation | N/A | 1. Login to the application as a registered user. 2. Ensure email notifications are enabled in user settings. 3. Navigate to the "Promotions" or "Marketing Preferences" section. 4. Ensure user is subscribed to promotional emails. 5. Wait for a promotional email to arrive. 6. Check inbox for the promotional email. |  |  | Passed
4 |  |  | Push Notifications | Verify that push notifications are sent. | User should receive push notifications. | Found as per expectation | N/A | 1. Login to the application as a registered user. 2. Ensure push notifications are enabled in user settings. 3. Perform an action that triggers a push notification (e.g., placing an order, account update). 4. Wait for the push notification to appear. 5. Check the device for the received notification. |  |  | Passed
5 |  |  | Mark Notifications as Read | Verify marking notifications as read | Notifications should be marked as read | Found as per expectation | N/A | 1. Login to the application as a registered user. 2. Go to the notifications section. 3. Receive multiple notifications. 4. Click or swipe on the notification to mark it as read. 5. Confirm that the notification is marked as read and removed from the unread section. |  |  | Passed
6 |  | Usability | Visibility of Notifications | Verify that notifications are visible to the user | Notifications should be visible when triggered | Found as per expectation | N/A | 1. Login to the application as a registered user. 2. Ensure notifications are enabled in settings. 3. Perform actions that trigger notifications (e.g., order updates, messages). 4. Wait for notifications to be triggered. 5. Verify that notifications are visible on the screen when triggered. |  |  | Passed
7 | Regster | Functionality Testing | Valid Email & Password | Verify registration with valid email and password | User should be successfully registered | Found as per expectation | Email: valid@example.com, Password: validpassword123 | 1. Enter valid credentials. 2. Click "Register" | N/A | N/A | Passed
8 |  |  | Invalid Email Format | Verify registration with an invalid email format | "Invalid email address" error message should appear | Found as per expectation | Email: invalidemail@domain, Password: validpassword123 | 1. Enter invalid email. 2. Enter valid password. 3. Click "Register" | N/A | N/A | Passed
9 |  |  | Empty Fields | Verify registration with empty email and password fields | "Email and Password are required" error message should appear | found as per expectation | N/A | 1. Leave email and password fields empty. 2. Click "Register" | N/A | N/A | Passed
10 |  |  | Duplicate Email | Verify registration with an already registered email | "Email already in use" error message should appear | found as per expectation | Email: ABC@gmail.com, Password: validpassword123 | 1. Enter email already used for registration. 2. Enter valid password. 3. Click "Register" |  |  | Passed
11 |  |  | Social Sign-In Conflict | Verify registration for an email used for social sign-in (e.g., Google or Facebook) | "Email already in use with social sign-in" error message should appear | found as per expectation | N/A |  |  |  | Passed
12 |  |  | Weak Password | Verify registration with a weak password (less than 8 characters) | "Password must be at least 8 characters" error message should appear | found as per expectation | Email: ABC@gmail.com, Password: 123 | 1. Enter valid email and weak password. 2. Click "Register" |  |  | Passed
13 |  |  | Terms and Conditions | Verify registration cannot proceed without accepting terms and conditions | "You must accept the terms and conditions" error message should appear | found as per expectation | N/A | 1. Try registering without accepting terms and conditions. 2. Observe error message |  |  | Passed
14 | Log In | Functionality Testing | Valid Email & Password | Verify login with valid email and password | User should be successfully signed in | Found as per expectation | Email: nurnishe999@gmail.com, Password: validpassword123 | 1. Enter valid email and password. 2. Click "Sign In" |  |  | Passed
15 |  |  | Invalid Email Format | Verify login with invalid email address | "Invalid email address" error message should appear | Found as per expectation | Email: ABC@gmail.com, Password: validpassword123 | 1. Enter invalid email and valid password. 2. Click "Sign In" |  |  | Passed
16 |  |  | Invalid Password | Verify login with an incorrect password | "Incorrect password" error message should appear | found as per expectation | Email: ABC@gmail.com, Password: invalidpassword | 1. Enter valid email and invalid password. 2. Click "Sign In" |  |  | Passed
17 |  |  | Empty Fields | Verify the "Sign In" button is disabled when the email and password fields are empty | "Sign In" button should be disabled | found as per expectation | N/A | 1. Leave email and password fields empty. 2. Observe "Sign In" button status |  |  | Passed
18 |  |  | Account Suspended | Verify that the "Account is permanently suspended" message appears for suspended accounts | The message should indicate the account is suspended | found as per expectation | N/A | 1. Attempt to sign in with a suspended account. 2. Check for the suspension message |  |  | Passed
19 |  |  | Appeal Form Link | Verify the "Go to appeal form" link redirects to the appeal page | User should be redirected to the appeal form page | found as per expectation | N/A | 1. Click on "Go to appeal form". 2. Observe redirection to appeal form page |  |  | Passed
20 |  |  | Stay Signed In | Verify that users remain signed in after checking the "Stay signed in" checkbox | User should remain signed in after closing and reopening the browser | found as per expectation | N/A | 1. Check "Stay signed in" box. 2. Enter valid credentials. 3. Click "Sign In". 4. Close and reopen browser. |  |  | Passed
21 |  |  | Social Media Login | Verify that users can log in using Google account | User should be logged in using Google credentials | found as per expectation | N/A | 1. Click "Continue with Google". 2. Log in using Google credentials |  |  | Passed
22 | Forgot password | Functionality Testing | Invalid Email | Verify that an error message is shown when the email does not exist in the system | "Email not found" or equivalent error message should appear | Found as per expectation | Email:abcgmail.com | 1. Click on "Forgot your password?". 2. Enter an invalid email address. 3. Observe the error message |  |  | Passed
23 |  |  | Reset Link | Verify that the password reset email contains a valid reset link | The email should contain a valid reset password link | Found as per expectation | Email: abc@example.com | 1. Enter valid email for password reset. 2. Check the reset email for the reset link |  |  | Passed
24 |  |  | Expired Reset Link | Verify that an error message is shown if the password reset link has expired | "This link has expired" error message should appear | Found as per expectation | Email: abc@example.com | 1. Request password reset. 2. Wait for a set time (e.g., 24 hours). 3. Click on the expired link |  |  | Passed
25 |  |  | Invalid Reset Link | Verify that an error message is shown when clicking on an invalid password reset link | "Invalid or expired link" error message should appear | Found as per expectation | Email: abc@example.com | 1. Request password reset. 2. Click on an invalid or manipulated link |  |  | Passed
26 |  |  | New Password Entry | Verify that the user can enter a new password after clicking the reset link | User should be able to enter and confirm the new password | Found as per expectation | New Password: newpassword123 | 1. Click the reset link. 2. Enter and confirm a new password. 3. Submit |  |  | Passed
27 |  |  | Successful Reset | Verify that the user can log in after successfully resetting the password | User should be able to log in with the new password | Found as per expectation | Email: abc@example.com, New Password: newpassword123 | 1. Reset the password. 2. Log in with the new password. |  |  | Passed
28 |  | Usability Testing | Forgot Password Link | Verify that the "Forgot your password?" link is visible on the sign-in page | The "Forgot your password?" link should be visible and clickable | Found as per expectation | N\A | 1. Navigate to the sign-in page. 2. Verify the "Forgot your password?" link is present |  |  | Passed
29 | Shipping | Functionality Testing | Add New Address | Verify that users can add a new shipping address. | New address should be added successfully. | Found as per expectation | N/A |  |  |  | Passed
30 |  |  | Select Saved Address | Verify that users can select a saved address. | Saved address should be selected successfully. | Not found as per expectation | N/A | 1. Goto the URL https://www.etsy.com/ 2. Select a product and order 3. Fill all the fiels with invalid credential 4.Check the save address for later checkbox | https://drive.google.com/file/d/1q6RiqLjKkD8Ddcl38uXnwRQ5Lzr2E1g3/view?usp=sharing |  | Failed
31 |  |  | Invalid Zip Code | Verify system validation for an invalid zip code. | Error message should be displayed for an invalid zip code. | Found as per expectation | N/A |  |  |  | Passed
32 | Footer | Functionality Testing | Footer Links | Verify footer links (Shop, Sell, About, Help) are visible and clickable | Links should be visible, clickable, and navigate to the respective pages | Found as per expectation | N/A | 1. Open the website. 2. Scroll to the footer section. 3. Click on each link and verify navigation. |  |  | Passed
33 |  |  | Button Click | Verify "Download the Etsy App" button navigates to the correct app download page | The user should be redirected to the Etsy app download page | Found as per expectation | N/A | 1. Scroll to the footer. 2. Click the "Download the Etsy App" button. 3. Verify redirection to app store page. |  |  | Passed
34 |  |  | Social Media | Verify the social media icons (Instagram, Facebook, Pinterest, YouTube) in the footer are clickable and lead to the correct pages | Each social media icon should open the corresponding social media page | Found as per expectation | N/A | 1. Scroll to the footer. 2. Click on each social media icon (Instagram, Facebook, Pinterest, YouTube). 3. Verify the redirection to the respective social media page. |  |  | Passed
|  |  | Language/Region Selector | Verify that the language and region selector displays the correct options | The region and language should be changeable using the dropdowns | Found as per expectation | N/A | 1. Scroll to the footer. 2. Check for the language/region selector. 3. Change the region and verify the site updates to the selected region. |  |  | Passed
35 | Sign Up | Functionality Testing | Valid Signup | Verify that users can sign up with valid details. | User should sign up successfully. | Found as per expectation | N/A |  |  |  | Passed
36 |  |  | Duplicate Email | Verify validation for duplicate email during signup. | Error message should be displayed for duplicate email. | Found as per expectation | N/A |  |  |  | Passed
37 |  |  | Invalid Email Format | Verify validation for an invalid email format. | Error message should be displayed for an invalid email format. | Found as per expectation | N/A |  |  |  | Passed
38 | Cart | Functionality Testing | Add Item | Verify that users can add items to the cart. | Item should be added to the cart successfully. | Found as per expectation | N/A | 1. Go to the product page. 2. Click on "Add to Cart" |  |  | Passed
39 |  |  | Item Count | Verify that item count increases after adding an item | Cart item count should increase by 1 | Found as per expectation | N/A | 1. Add an item to the cart. 2. Check the cart icon for item count |  |  | Passed
40 |  |  | Remove Item | Verify user can remove an item from the cart | Item should be successfully removed | Found as per expectation | N/A | 1. Open cart. 2. Click the remove button next to an item. |  |  | Passed
41 |  |  | Empty Cart | Verify cart is empty after removing all items | "Your cart is empty" message should be displayed | Found as per expectation | N/A | 1. Remove all items from cart. 2. Check cart message |  |  | Passed
42 |  |  | Quantity Update | Verify that item quantity is updated correctly | Item quantity and total price should update correctly | Found as per expectation | N/A | 1. Open cart. 2. Change item quantity. 3. Observe cart total. |  |  | Passed
44 |  |  | Price Calculation | Verify that total price is calculated correctly | Total price should reflect correctly after quantity updates | Found as per expectation | N/A | 1. Add product to cart. 2. Check if total price is calculated correctly. |  |  | Passed
45 |  |  | Discount Code | Verify user can apply a valid discount code | Discount should be applied and total should reduce | Found as per expectation | N/A | 1. Add item to cart. 2. Enter coupon code at checkout. 3. Check total price. |  |  | Passed
46 |  |  | Checkout | Verify user can proceed to checkout page | User should be redirected to checkout page | Found as per expectation | N/A | 1. Add items to cart. 2. Click "Proceed to Checkout." |  |  | Passed
47 | Search | Functionality Testing | Search with Valid Input | Verify search returns relevant results for valid input | Relevant results should appear for the entered query | Found as per expectation | N/A | 1. Enter a valid search term. 2. Hit Enter or click Search. |  |  | Passed
48 |  |  | Search with Invalid Input | Verify search handles invalid input gracefully | "No results found" or a similar message should appear | Found as per expectation | Search Term: "xyz123abc" | 1. Enter an invalid search term. 2. Observe the result page. |  |  | Passed
49 |  |  | Search with Empty Input | Verify that no search is performed and an error or prompt appears when the input is empty | No results or error message asking for input should appear | Found as per expectation | N/A | 1. Leave the search bar empty. 2. Click Search. | empty search |  | Failed
50 |  |  | Auto-Suggestions | Verify that search bar displays relevant suggestions as user types | Suggestions should appear relevant to the input | Found as per expectation | N/A | 1. Type "W" in the search bar. 2. Check if suggestions related to "W" appear. |  |  | Passed
51 |  |  | Search Button | Verify that the search button works properly | Search should execute on button click and return results | Found as per expectation | N/A | 1. Type in a search term. 2. Click the Search button. |  |  | Passed
52 |  |  | Reset Search | Verify that search bar is cleared after performing a search | The search bar should be cleared after a search is executed | Found as per expectation | N/A | 1. Type in a search term. 2. Click search. 3. Check if search term is cleared |  |  | Passed
53 |  |  | Special Characters | Verify search handles special characters correctly | Special characters should be accepted and return relevant results | Found as per expectation | N/A | 1. Enter a search term with special characters. 2. Check if results appear. |  |  | Passed
54 |  |  | Autocomplete | Verify that autocomplete suggests relevant search terms as the user types | Suggestions should appear based on the first few characters typed | Found as per expectation | N/A | 1. Start typing "W" in the search bar. 2. Observe autocomplete suggestions. |  |  | Passed
55 | Payment | Functionality Testing | Credit Card | Verify that users can pay with a credit card | Payment should be processed successfully. | Found as per expectation | N/A |  |  |  | Passed
56 |  |  | Paypal | Verify that users can pay with PayPal. | Payment should be processed successfully. | Found as per expectation | N/A |  |  |  | Passed
57 |  |  | Invalid Card Credentials | Verify validation for invalid card credentials. | Error message should be displayed for invalid card credentials. | Found as per expectation | N/A |  |  |  | Passed

## Test Matrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (31/31)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (31/31)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (25/31)*100 = 80.64
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (5/31)*100 = 16.12
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/31)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A

## Bug Report
Bug Reporting
# SL 43
Issue: Saved address should be selected successfully.
Reproducing Steps:
1. Goto the URL https://www.etsy.com/ 2. Select a product and order 3. Fill all the fiels with invalid credential 4.Check the save address for later checkbox
Env: Production
Module: Shipping
Severity: P1
Screenshot: Invalid email address error
Responsible QA: MD Shalim Sadman